## Sheet1
Bid Item | Task Name | % Complete | Duration | Start | Finish
1.01 | Notice to Proceed | 100% | 0.8 days | Mon 11/24/25 | Mon 11/24/25
1.01 | Mobilization | 50% | 4 days | Mon 12/8/25 | Fri 12/12/25
6.01 | Install Temporary Railroad Crossing | 100% | 12 days | Tue 12/16/25 | Tue 1/6/26
1.06 | Install Swamp Mat Access Road | 100% | 1 day | Mon 1/5/26 | Tue 1/6/26
6.02 | Replace Vault 1 | 100% | 1 day | Tue 1/6/26 | Wed 1/7/26
6.02 | Replace Vault 2 | 100% | 1 day | Wed 1/7/26 | Thu 1/8/26
6.03 | Remove Access Mats and Restore Area | 1% | 20 days | Thu 1/8/26 | Thu 2/12/26
6.04 | Transport Material to Spoil Management | 0% | 20 days | Thu 1/8/26 | Thu 2/12/26
8.01 | Restore Area (East Slope) | 0% | 20 days | Thu 1/8/26 | Thu 2/12/26
1.05 | Clear and Strip Access Alignment | 100% | 1 day | Fri 12/19/25 | Mon 12/22/25
5.09 | Install Stream Crossing and Pump Around | 0% | 6 days | Thu 1/15/26 | Mon 1/26/26
5.03 | Drill Sumps SB 9 8 and 7 | 0% | 1 day | Fri 1/16/26 | Mon 1/19/26
5.02 | Excavate Trench STA 6+93 to Vault 4 | 0% | 0.5 days | Mon 1/19/26 | Tue 1/20/26
5.05 | Install 4in SDR11 HDPE Pipe | 0% | 1 day | Tue 1/20/26 | Wed 1/21/26
5.06 | Backfill with No8 Stone | 0% | 1 day | Wed 1/21/26 | Thu 1/22/26
5.1 | Set 5x5x4 Vaults | 0% | 1 day | Thu 1/22/26 | Fri 1/23/26
5.08 | Install GCL Liner | 0% | 1 day | Fri 1/23/26 | Tue 1/27/26
5.05 | Install Airline and Water Conveyance Lines | 0% | 1 day | Tue 1/27/26 | Wed 1/28/26
5.07 | Backfill Trench with Native Fill | 0% | 1 day | Wed 1/28/26 | Thu 1/29/26
5.11 | Install Mechanical Components in Vaults | 0% | 2 days | Thu 1/29/26 | Tue 2/3/26
5.12 | Develop Wells | 0% | 10 days | Tue 2/3/26 | Thu 2/19/26
8.01 | Restore Area (Southern Bench) | 0% | 1 day | Thu 1/29/26 | Fri 1/30/26
5.13 | Place Excess Sediment Material | 0% | 0.4 days | Thu 1/29/26 | Fri 1/30/26
5.14 | Transport Material to Spoil Management | 0% | 0.4 days | Thu 1/29/26 | Fri 1/30/26
1.05 | Clearing Grubbing and Chipping | 50% | 1 day | Tue 2/3/26 | Wed 2/4/26
1.03 | Install Filter Socks and RCE | 0% | 1 day | Wed 2/4/26 | Thu 2/5/26
1.06 | Develop Temp Access Road | 0% | 2 days | Thu 2/5/26 | Tue 2/10/26
3.01 | Excavate Grade and Backfill Embankment | 0% | 4 days | Tue 2/10/26 | Tue 2/17/26
3.02 | Install 10oz Geotextile | 0% | 1 day | Tue 2/17/26 | Wed 2/18/26
3.03 | Install Rip Rap Aggregate | 0% | 3 days | Wed 2/18/26 | Tue 2/24/26
8.01 | Restore Area (Roadside Slope) | 0% | 0.4 days | Tue 2/24/26 | Tue 2/24/26
3.04 | Place Excess Sediment Material | 0% | 0.4 days | Tue 2/24/26 | Tue 2/24/26
3.05 | Transport Material to Spoil Management | 0% | 0.4 days | Tue 2/24/26 | Tue 2/24/26
4.01 | Remove Existing Culvert and Excavate Trench | 0% | 1 day | Tue 2/24/26 | Wed 2/25/26
4.03 | Install Headwall(s) | 12% | 1 day | Fri 2/20/26 | Wed 2/25/26
4.01 | Install 30in Culvert | 0% | 1 day | Wed 2/25/26 | Thu 2/26/26
4.02 | Place Geotextile and Rip Rap | 0% | 1 day | Wed 2/25/26 | Thu 2/26/26
2.01 | S-2 Ditch Excavate and Grade Channel | 0% | 0.8 days | Thu 2/26/26 | Fri 2/27/26
2.05 | S-2 Ditch Install Rip Rap | 0% | 0.8 days | Fri 2/27/26 | Mon 3/2/26
2.01 | S-1 Ditch Excavate and Grade Channel | 0% | 1 day | Mon 3/2/26 | Tue 3/3/26
2.05 | S-1 Ditch Install Rip Rap | 0% | 1 day | Tue 3/3/26 | Wed 3/4/26
2.04 | Deploy ECB on Berm | 0% | 0.4 days | Wed 3/4/26 | Thu 3/5/26
2.02 | Place Native Streambed Material | 0% | 0.8 days | Mon 3/2/26 | Tue 3/3/26
2.03 | Install Geotextile | 0% | 0.8 days | Mon 3/2/26 | Tue 3/3/26
2.06 | Place Excess Sediment Material | 0% | 0.8 days | Tue 3/3/26 | Wed 3/4/26
2.07 | Transport Material to Spoil Management | 0% | 0.8 days | Tue 3/3/26 | Wed 3/4/26
7.01 | Interim Stockpiling and Dewatering | 0% | 1.6 days | Mon 3/2/26 | Wed 3/4/26
7.02 | Spread Grade and Compact Material | 0% | 1.6 days | Wed 3/4/26 | Fri 3/6/26
7.03 | Geosynthetic Clay Liner | 0% | 0.8 days | Wed 3/4/26 | Thu 3/5/26
7.04 | Soils Cover Placement | 0% | 0.4 days | Fri 3/6/26 | Fri 3/6/26
7.05 | Top Soil Cover Import and Placement | 0% | 0.4 days | Fri 3/6/26 | Mon 3/9/26
8.02 | Permanent Stabilization | 0% | 1 day | Mon 4/6/26 | Tue 4/7/26
8.03 | Wetland Restoration | 0% | 1 day | Fri 3/6/26 | Tue 3/10/26
1.01 | Demobilization | 0% | 2 days | Tue 3/10/26 | Thu 3/12/26
1.02 | As-Built Survey | 0% | 4 days | Tue 3/3/26 | Tue 3/10/26